## Gantt Chart
GANTT CHART TEMPLATE | [7 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | COVID-19 Dashboard | [5 empty] | COMPANY NAME | [8 empty] | CTEM46
PROJECT MANAGER |  | Chu Siu Kay Alan | [5 empty] | DATE | [8 empty] | 2020-05-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | SPRINT ONE | [13 empty] | SPRINT TWO | [13 empty] | SPRINT THREE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
[7 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[7 empty] | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | Project Initiation
1.1 | Formuling Brief | Alan C | 2020-06-14 | 2020-06-14 | 0 | 20% | bar: WEEK 1 14 S to WEEK 1 15 M
1.2 | Data Acquisition | Alan C | 2020-06-14 | 2020-06-14 | 0 | 20% | bar: WEEK 1 15 M
1.3 | Data Analysis | Alan C | 2020-06-14 | 2020-06-14 | 0 | 0% | bar: WEEK 1 15 M to WEEK 1 17 W
1.4 | Literature Review | Alan C | 2020-06-14 | 2020-06-14 | 0 | 0% | bar: WEEK 1 18 R to WEEK 2 22 M
1.5 | System Requirements | Alan C | 2020-06-14 | 2020-06-14 | 0 | 0% | bar: WEEK 2 23 T to WEEK 2 27 S
2 | Product Development
2.1 | Product Design | Alan C | 2020-06-14 | 2020-06-14 | 4 | 0% | bar: WEEK 3 28 S to WEEK 3 30 T
2.1 | Product Implementation | Alan C | 2020-06-14 | 2020-06-14 | 4 | 0% | bar: WEEK 3 30 T to WEEK 4 7 T
2.2 | System Test | Alan C | 2020-06-14 | 2020-06-14 | 3 | 0% | bar: WEEK 4 8 W to WEEK 4 11 S
2.3 | Writing Report | Alan C | 2020-06-14 | 2020-06-14 | 0 | 0% | bar: WEEK 5 12 S to WEEK 5 17 F