## Gantt Chart
GANTT CHART TEMPLATE | [7 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | COVID-19 Dashboard | [5 empty] | COMPANY NAME | [8 empty] | CTEM46
PROJECT MANAGER |  | Chu Siu Kay Alan | [5 empty] | DATE | [8 empty] | 2020-05-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | SPRINT ONE | [13 empty] | SPRINT TWO | [13 empty] | SPRINT THREE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
[7 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[7 empty] | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | Project Conception and Initiation
1.1 | Project Charter | Alan C | 2020-05-10 | 2020-05-14 | 4 | 20% | bar: WEEK 1 10 S to WEEK 1 14 R; WEEK 2 17 S to WEEK 2 23 S
1.2 | Research on datasets | Alan C | 2020-05-13 | 2020-05-18 | 5 | 0% | bar: WEEK 1 13 W to WEEK 2 23 S
1.3 | Literature Review | Alan C | 2020-05-15 | 2020-05-23 | 8 | 0% | bar: WEEK 1 15 F to WEEK 2 23 S
2 | Project Definition and Planning
2.1 | Literature Review | Alan C | 2020-05-24 | 2020-05-27 | 4 | 0% | bar: WEEK 2 17 S to WEEK 3 27 W
2.1 | Scope and Goal Setting | Alan C | 2020-05-26 | 2020-05-27 | 4 | 0% | bar: WEEK 2 17 S to WEEK 2 23 S; WEEK 3 26 T to WEEK 3 27 W
2.2 | Project Plan | Alan C | 2020-05-27 | 2020-05-28 | 3 | 0% | bar: WEEK 2 17 S to WEEK 2 23 S; WEEK 3 27 W to WEEK 3 28 R
2.3 | Literature Review Report | Alan C | 2020-05-28 | 2020-06-12 | 0 | 0% | bar: WEEK 2 17 S to WEEK 2 23 S; WEEK 3 28 R to WEEK 5 12 F